## Sheet1
گزارش وضعیت ارزش کسب شده EV
عنوان پروژه : |  | تاریخ تهیه :
بودجه تا زمان تکمیل : |  | وضعیت کلی :
| دوره گزارش گیری فعلی (جاری) | مقدار تجمعی تا این دوره گزارش | مقدار تجمعی تا دوره گزارش گیری قبلی
ارزش برنامه ریزی شده (PV یا BCWS)
ارزش کسب شده (EV یا BCWP)
هزینه واقعی (AC یا ACWP)
انحراف برنامه (SV)
انحراف هزینه (CV)
شاخص عملکرد برنامه (SPI)
شاخص عملکرد هزینه (CPI)
دلایل ریشه ای انحراف برنامه:
شدت اثر روی تحویل شدنی ها، مایلستون ها یا مسیر بحرانی :
دلایل ریشه ای انحرافات هزینه :
شدت اثر روی بودجه، بودجه های (وجوه) احتیاطی یا ذخیره :
درصد برنامه ریزی شده
درصد کسب شده
درصد مصرف شده
برآوردهای هزینه کل تا زمان تکمیل پروژه (EAC):
EAC w/CPI [BAC/CPI]
EAC w/ CPIxSPI [AC+((BAC-EV)/(CPIxSPI))]
EAC منتخب و توجیه و تفسیر آن :
شاخص عملکرد تا تکمیل پروژه (TCPI)

## Sheet2
Parametric Estimates
WBS ID | Effort Hours | Resource Quantity | % available | Performance factor | Duration Estimate
1.1 | 150 | 2 | 75% | 80% | 125
Analogous Estimates
WBS ID | Prior activity | Prior Variable | Duration | Current variable | Multiplier | Duration Estimate
1.1 | Build deck | 160 sq. ft. | 10 days | 200 sq. ft. | 1.25 | 12.5
Three Point Estimates
WBS ID | Optimistic estimate | Most likely estimate | Pessimistic estimate | Weighting factor | Expected Duration Estimate
1.1 | 20 | 25 | 36 | (o+4m+p)/6 | 26